## Template 1
Strategy | Activity | Resources
Audit and feedback | Meet with stakeholders to identify outcomes | Project officer
| Retrieve and analyse data on outcomes | Team leader A
| Present data to stakeholders | Team leader B
Clinical team A - champion
Clinical team B - champion
Involve existing governing structures | Meet with executives | Project officer
| Meet with clinical team/s | Executive A
Executive B
Team leader A
Team leader B
Identify and prepare champions | Engage with stakeholders to identify potential champions | Project officer
| Engage (meetings or emails) with possible champions | Team leader A
| Ongoing support for champions | Team leader B
Clinical team A - champion
Clinical team B - champion
Train-the-trainer | Adapt training with stakeholders | Project officer
| Train the champions to be trainers | Team leader A
| Create opportunities for the trainers to train others | Team leader B
| Monitor training progress | Clinical team A - champion
Clinical team B - champion
| Training material | Training material
| Training room | Training room

## Template 2
Site | Phase | Date | Activity | Purpose | Strategy | Resource- Category | Resource | Hourly wage rate | Number of personnel involved | Time spent per person (hours) | Total person (hours) | Cost ($) | Labour/ Non-Labour | Data source
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | site team | Executive A | 113.8664 | 1 | 0.5 | 0.5 | 56.9332 | labour | project documents- field notes
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | site team | Executive B | 126.5182 | 1 | 0.5 | 0.5 | 63.2591 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | site team | Team leader A | 88.5628 | 1 | 0.5 | 0.5 | 44.2814 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | site team | Team leader B | 101.2146 | 1 | 0.5 | 0.5 | 50.6073 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | project team | Project officer | 75.9109 | 1 | 1 | 1 | 75.9109 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | site team | Team leader A | 88.5628 | 1 | 1 | 1 | 88.5628 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | site team | Team leader B | 101.2146 | 1 | 1 | 1 | 101.2146 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | email asking for champion suggestions | Identify and prepare champions | project team | Project officer | 75.9109 | 1 | 0.16667 | 0.16667 | 12.6518 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | site team | Team leader A | 88.5628 | 1 | 0.16667 | 0.16667 | 14.7605 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | site team | Team leader B | 101.2146 | 1 | 0.16667 | 0.16667 | 16.8691 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | site team | Clinical team A - champion | 69.585 | 1 | 0.5 | 0.5 | 34.7925 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | site team | Clinical team B - champion | 50.6073 | 1 | 0.5 | 0.5 | 25.3036 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 1 | 1 | 75.9109 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | site team | Team leader A | 88.5628 | 1 | 1 | 1 | 88.5628 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | site team | Team leader B | 101.2146 | 1 | 1 | 1 | 101.2146 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | site team | Clinical team A - champion | 69.585 | 1 | 1 | 1 | 69.585 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | site team | Clinical team B - champion | 50.6073 | 1 | 1 | 1 | 50.6073 | labour | project documents- field notes
1 | pre | 2072-01-25 | Adapt training with stakeholders | Incorporate adaptations to training | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 1 | 1 | 75.9109 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 1 | 1 | 75.9109 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | site team | Clinical team A - champion | 69.585 | 1 | 1 | 1 | 69.585 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | site team | Clinical team B - champion | 50.6073 | 1 | 1 | 1 | 50.6073 | labour | project documents- field notes
1 | pre | 2072-02-05 | Training material | Train the champions to be trainers | Train-the-trainer | project team | Training material | 50 | 5 | 1 | 5 | 250 | non-labour | project documents- field notes
1 | pre | 2072-02-05 | Training room | Train the champions to be trainers | Train-the-trainer | project team | Training room | 900 | 1 | 1 | 1 | 900 | non-labour | project documents- field notes
1 | during | 2072-02-07 | Create opportunities for the trainers to train others | book meeting room for monthly training sessions for champions to train | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 0.25 | 0.25 | 18.9777 | labour | project documents- field notes
1 | during | 2072-02-08 | Ongoing support for champions | check in with champions | Identify and prepare champions | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | during | 2072-02-09 | Monitor training progress | request current training numbers | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 0.16667 | 0.16667 | 12.6518 | labour | project documents- field notes
1 | during | 2072-02-25 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | during | 2072-02-25 | Ongoing support for champions | check in with champions | Identify and prepare champions | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | during | 2072-02-26 | Monitor training progress | request current training numbers | Train-the-trainer | project team | Project officer | 75.9109 | 1 | 0.16667 | 0.16667 | 12.6518 | labour | project documents- field notes
1 | during | 2072-03-08 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | project team | Project officer | 75.9109 | 1 | 0.5 | 0.5 | 37.9555 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | site team | Clinical team A - champion | 69.585 | 1 | 0.5 | 0.5 | 34.7925 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | site team | Clinical team B - champion | 50.6073 | 1 | 0.5 | 0.5 | 25.3036 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | site team | Team leader A | 88.5628 | 1 | 0.5 | 0.5 | 44.2814 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | site team | Team leader B | 101.2146 | 1 | 0.5 | 0.5 | 50.6073 | labour | project documents- field notes

## Template 3
Resource- labour | Resource- category | Position | Annual salary | Hrly | Hrly +25% oncost | Classification | Source | Link
Project officer | project team |  | 120000 | 60.7287 | 75.9109
Executive A | site team |  | 180000 | 91.0931 | 113.8664
Executive B | site team |  | 200000 | 101.2146 | 126.5182
Team leader A | site team |  | 140000 | 70.8502 | 88.5628
Team leader B | site team |  | 160000 | 80.9717 | 101.2146
Clinical team A - champion | site team |  | 110000 | 55.668 | 69.585
Clinical team B - champion | site team |  | 80000 | 40.4858 | 50.6073
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Resource- non-labour | Resource- category | Cost type | Source | Cost year | Unit price
Training material | project team | Monetary | Invoice | 2023 | 50
Training room | project team | Monetary | Market value | 2023 | 900

## Analysis example- Pivot Table
Sum of Cost ($) | Column Labels |  |  |  |  | Sum of Cost ($) | Column Labels
Row Labels | Audit and feedback | Identify and prepare champions | Involve existing governing structures | Train-the-trainer | Grand Total | Row Labels | labour | non-labour | Grand Total
project team | 189.7773 | 164.4737 | 75.9109 | 1422.0142 | 1852.1761 | Train-the-trainer | 702.1761 | 1150 | 1852.1761
Training room |  |  |  | 900 | 900 | Audit and feedback | 534.5395 |  | 534.5395
Project officer | 189.7773 | 164.4737 | 75.9109 | 272.0142 | 702.1761 | Involve existing governing structures | 290.9919 |  | 290.9919
Training material |  |  |  | 250 | 250 | Identify and prepare champions | 256.1994 |  | 256.1994
site team | 344.7621 | 91.7257 | 215.081 | 430.1619 | 1081.7308 | Grand Total | 1783.9069 | 1150 | 2933.9069
Team leader B | 151.8219 | 16.8691 | 50.6073 | 101.2146 | 320.5128
Team leader A | 132.8441 | 14.7605 | 44.2814 | 88.5628 | 280.4487
Clinical team A - champion | 34.7925 | 34.7925 |  | 139.17 | 208.7551
Clinical team B - champion | 25.3036 | 25.3036 |  | 101.2146 | 151.8219
Executive B |  |  | 63.2591 |  | 63.2591
Executive A |  |  | 56.9332 |  | 56.9332
Grand Total | 534.5395 | 256.1994 | 290.9919 | 1852.1761 | 2933.9069