## Template 1
Strategy | Activities | Resources
Audit and feedback | Meet with stakeholders to identify outcomes | Project officer
| Retrieve and analyse data on outcomes | Team leader A
| Present data to stakeholders | Team leader B
Clinical team A - champion
Clinical team B - champion
Involve existing governing structures | Meet with executives | Project officer
| Meet with clinical team/s | Executive A
Executive B
Team leader A
Team leader B
Identify and prepare champions | Engage with stakeholders to identify potential champions | Project officer
| Engage (meetings or emails) with possible champions | Team leader A
| Ongoing support for champions | Team leader B
Clinical team A - champion
Clinical team B - champion
Train-the-trainer | Adapt training with stakeholders | Project officer
| Train the champions to be trainers | Team leader A
| Create opportunities for the trainers to train others | Team leader B
| Monitor training progress | Clinical team A - champion
Clinical team B - champion
| Training material | Training material
| Training room | Training room

## Template 2A
Site | Phase | Date | Activity | Purpose | Strategy | Role | Role- Category | Hourly wage rate | Number of personnel involved | Time spent per person (mins) | Total person minutes | Cost ($) | Labour/ Non-Labour | Data source
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Executive A | site team | 130.4348 | 1 | 30 | 30 | 65.2174 | labour | project documents- field notes
1 | pre | 2072-01-01 | Meet with executives | present intervention aims and outcomes | Involve existing governing structures | Executive B | site team | 144.9275 | 1 | 30 | 30 | 72.4638 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Team leader A | site team | 101.4493 | 1 | 30 | 30 | 50.7246 | labour | project documents- field notes
1 | pre | 2072-01-02 | Meet with clinical team/s | present intervention aims and outcomes | Involve existing governing structures | Team leader B | site team | 115.942 | 1 | 30 | 30 | 57.971 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Project officer | project team | 86.9565 | 1 | 60 | 60 | 86.9565 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Team leader A | site team | 101.4493 | 1 | 60 | 60 | 101.4493 | labour | project documents- field notes
1 | pre | 2072-01-09 | Meet with stakeholders to identify outcomes | meeting to identify what needs to be audited and how to feed it back | Audit and feedback | Team leader B | site team | 115.942 | 1 | 60 | 60 | 115.942 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | email asking for champion suggestions | Identify and prepare champions | Project officer | project team | 86.9565 | 1 | 10 | 10 | 14.4928 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | Team leader A | site team | 101.4493 | 1 | 10 | 10 | 16.9082 | labour | project documents- field notes
1 | pre | 2072-01-11 | Engage with stakeholders to identify potential champions | champion suggested via email | Identify and prepare champions | Team leader B | site team | 115.942 | 1 | 10 | 10 | 19.3237 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team A champion | Identify and prepare champions | Clinical team A - champion | site team | 79.7101 | 1 | 30 | 30 | 39.8551 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | pre | 2072-01-12 | Engage (meetings or emails) with possible champions | met with clinical team B champion | Identify and prepare champions | Clinical team B - champion | site team | 57.971 | 1 | 30 | 30 | 28.9855 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 60 | 60 | 86.9565 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Team leader A | site team | 101.4493 | 1 | 60 | 60 | 101.4493 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Team leader B | site team | 115.942 | 1 | 60 | 60 | 115.942 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Clinical team A - champion | site team | 79.7101 | 1 | 60 | 60 | 79.7101 | labour | project documents- field notes
1 | pre | 2072-01-24 | Adapt training with stakeholders | discuss training with stakeholders and adapt to clinical context if needed | Train-the-trainer | Clinical team B - champion | site team | 57.971 | 1 | 60 | 60 | 57.971 | labour | project documents- field notes
1 | pre | 2072-01-25 | Adapt training with stakeholders | Incorporate adaptations to training | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 60 | 60 | 86.9565 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 60 | 60 | 86.9565 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | Clinical team A - champion | site team | 79.7101 | 1 | 60 | 60 | 79.7101 | labour | project documents- field notes
1 | pre | 2072-02-05 | Train the champions to be trainers | same as activity | Train-the-trainer | Clinical team B - champion | site team | 57.971 | 1 | 60 | 60 | 57.971 | labour | project documents- field notes
1 | pre | 2072-02-05 | Training material | Train the champions to be trainers | Train-the-trainer | Training material | project team | 50 | 5 | 60 | 300 | 250 | non-labour | project documents- field notes
1 | pre | 2072-02-05 | Training room | Train the champions to be trainers | Train-the-trainer | Training room | project team | 900 | 1 | 60 | 60 | 900 | non-labour | project documents- field notes
1 | during | 2072-02-07 | Create opportunities for the trainers to train others | book meeting room for monthly training sessions for champions to train | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 15 | 15 | 21.7391 | labour | project documents- field notes
1 | during | 2072-02-08 | Ongoing support for champions | check in with champions | Identify and prepare champions | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | during | 2072-02-09 | Monitor training progress | request current training numbers | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 10 | 10 | 14.4928 | labour | project documents- field notes
1 | during | 2072-02-25 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | during | 2072-02-25 | Ongoing support for champions | check in with champions | Identify and prepare champions | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | during | 2072-02-26 | Monitor training progress | request current training numbers | Train-the-trainer | Project officer | project team | 86.9565 | 1 | 10 | 10 | 14.4928 | labour | project documents- field notes
1 | during | 2072-03-08 | Retrieve and analyse data on outcomes | same as activity | Audit and feedback | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Project officer | project team | 86.9565 | 1 | 30 | 30 | 43.4783 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Clinical team A - champion | site team | 79.7101 | 1 | 30 | 30 | 39.8551 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Clinical team B - champion | site team | 57.971 | 1 | 30 | 30 | 28.9855 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Team leader A | site team | 101.4493 | 1 | 30 | 30 | 50.7246 | labour | project documents- field notes
1 | during | 2072-03-22 | Present data to stakeholders | ensure stakeholders are happy with progress, and address any issues | Audit and feedback | Team leader B | site team | 115.942 | 1 | 30 | 30 | 57.971 | labour | project documents- field notes

## Wages
Role | Role- category | Position | Annual salary | Hrly | Hrly +25% oncost | Classification | Source | Link
Project officer | project team |  | 120000 | 69.5652 | 86.9565
Executive A | site team |  | 180000 | 104.3478 | 130.4348
Executive B | site team |  | 200000 | 115.942 | 144.9275
Team leader A | site team |  | 140000 | 81.1594 | 101.4493
Team leader B | site team |  | 160000 | 92.7536 | 115.942
Clinical team A - champion | site team |  | 110000 | 63.7681 | 79.7101
Clinical team B - champion | site team |  | 80000 | 46.3768 | 57.971
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Training material | project team |  |  | 0 | 50 | 2023 | Invoice
Training room | project team |  |  | 0 | 900 | 2023 | Market value

## Pivot table
Sum of Cost ($) | Column Labels
Row Labels | Audit and feedback | Identify and prepare champions | Involve existing governing structures | Train-the-trainer | Grand Total
project team | 213.025 | 184.6217 | 86.0833 | 1455.3358 | 1939.0658
labour | 213.025 | 184.6217 | 86.0833 | 305.3358 | 789.0658
Project officer | 213.025 | 184.6217 | 86.0833 | 305.3358 | 789.0658
non-labour |  |  |  | 1150 | 1150
Training material |  |  |  | 250 | 250
Training room |  |  |  | 900 | 900
site team | 387.2048 | 103.323 | 248.7328 | 484.2624 | 1223.523
labour | 387.2048 | 103.323 | 248.7328 | 484.2624 | 1223.523
Clinical team A - champion | 39.4012 | 39.4012 |  | 157.605 | 236.4075
Clinical team B - champion | 28.4365 | 28.4365 |  | 113.746 | 170.619
Executive A |  |  | 67.0383 |  | 67.0383
Executive B |  |  | 75.2388 |  | 75.2388
Team leader A | 145.9371 | 16.2152 | 48.6457 | 97.2914 | 308.0894
Team leader B | 173.43 | 19.27 | 57.81 | 115.62 | 366.13
Grand Total | 600.2298 | 287.9446 | 334.816 | 1939.5982 | 3162.5887

## Summary table
Sum of Cost ($) | Column Labels |  |  |  |  | Sum of Cost ($) | Column Labels
Row Labels | Train-the-trainer | Audit and feedback | Involve existing governing structures | Identify and prepare champions | Grand Total | Row Labels | labour | non-labour | Grand Total
project team | 1455.3358 | 213.025 | 86.0833 | 184.6217 | 1939.0658 | Train-the-trainer | 789.5982 | 1150 | 1939.5982
Training room | 900 |  |  |  | 900 | Audit and feedback | 600.2299 |  | 600.2299
Project officer | 305.3358 | 213.025 | 86.0833 | 184.6217 | 789.0658 | Involve existing governing structures | 334.816 |  | 334.816
Training material | 250 |  |  |  | 250 | Identify and prepare champions | 287.9446 |  | 287.9446
site team | 484.2624 | 387.2048 | 248.7328 | 103.323 | 1223.523 | Grand Total | 2012.5887 | 1150 | 3162.5887
Team leader B | 115.62 | 173.43 | 57.81 | 19.27 | 366.13
Team leader A | 97.2914 | 145.9371 | 48.6457 | 16.2152 | 308.0894
Clinical team A - champion | 157.605 | 39.4012 |  | 39.4012 | 236.4075
Clinical team B - champion | 113.746 | 28.4365 |  | 28.4365 | 170.619
Executive B |  |  | 75.2388 |  | 75.2388
Executive A |  |  | 67.0383 |  | 67.0383
Grand Total | 1939.5982 | 600.2298 | 334.816 | 287.9446 | 3162.5887